## Retest Sheet
ID | State | Severity | Title | Group1 | Group2 | Group3
13769 | Assigned | Minor | JioSaavn Lite: Terms and Privacy Page not proper
13784 | Assigned | Normal | JioSaavn Lite: Reverse Scrolling in Terms and Privacy Page [Device Specific]
13785 | Assigned | Minor | JioSaavn Lite: On terms & privacy page, the JioSaavn logo is overlapping with the information
13786 | Assigned | Major | JioSaavn Lite: when the internet is off and you try to login with mobile no, the app Crashes
13787 | Assigned | Major | JioSaavn Lite: Though Song removed from library still shows in library
13788 | Assigned | Minor | JioSaavn Lite: The song and jiotune gets played simultaneously
13789 | Assigned | Minor | JioSaavn Lite : Copyright years are incorrectly written in several sections.
13790 | Assigned | Minor | JioSaavn Lite: In help and faq section inconsistencies are seen
13791 | Assigned | Normal | JioSaavn Lite: the page gets stuck on the loading page
13792 | Assigned | Normal | JioSaavn Lite: Advertisement is not showing in notification bar(Device Specific)
13793 | Assigned | Normal | JioSaavn Lite: play radio for carnatic is unresponsive
13794 | Assigned | Normal | JioSaavn Lite: Music player in notification panel disappears after clicking on pause and play button
13795 | Assigned | Minor | JioSaavn Lite: The pause button in the player in notification bar is cropped.
13796 | Assigned | Normal | JioSaavn Lite: Some Podcasts are unavailable and gives error as couldn't find
13797 | Assigned | Normal | JioSaavn Lite: The song played in previous account remains in the player when user logins using another account.
13799 | Assigned | Normal | JioSaavn Lite : Player disappears when opened from pop-up view
13800 | Assigned | Normal | JioSaavn Lite : On Sign up page, Terms of Service and Privacy Policy does not directs any where
13801 | Assigned | Normal | JioSaavn Lite: At the bottom, wrong tab heading is highlighted.
13802 | Assigned | Normal | JioSaavn Lite:When user logs out and tries to play song from notification bar , user sees a white page
13805 | Assigned | Major | JioSaavn Lite : When user tries to play a playlist by clicking on 'Play now', it doesn't play
13806 | Assigned | Minor | JioSaavn Lite : In setting the profile image outer circle is extremely towards right hence some part is cut
18015 | Assigned | Minor | JioSaavn Lite: There is an unprocessed image below the advertisement.
18016 | Assigned | Minor | JioSaavn Lite: The "privacy policy" link is missing when display language is Malayalam.
18017 | Assigned | Minor | JioSaavn Lite: '&' remains same in settings when app language is changed to Tamil
18018 | Assigned | Critical | JioSaavn Lite: App crashes when user clicks on channel radio
18019 | Assigned | Normal | JioSaavn Lite: Content in the app overlap with each other when user switches from split screen mode to normal mode.
18020 | Assigned | Minor | JioSaavn Lite: The username gets cropped in the Mylibrary section.(Enhancement)
18021 | Assigned | Minor | JioSaavn Lite: User gets automatically transferred to the "Genres" page when user has opened a channel in split screen mode.
18022 | Assigned | Minor | JioSaavn Lite: 'Surprise Me' text overlaps content on search page, when display language is Tamil
18023 | Assigned | Minor | JioSaavn Lite: The advertisement that appears after installing the app does not fit in the screen
18024 | Assigned | Critical | JioSaavn Lite: Clicking on request jiotune crashes the app.
18025 | Assigned | Normal | JioSaavn Lite: Music Language selections must also be in regional language not only English like app language section.
18026 | Assigned | Normal | JioSaavn Lite: Some texts and buttons in a podcast are in English when another display language is selected.
18027 | Assigned | Normal | JioSaavn Lite: For few songs the description and the song title is in english even though app language is marathi
18028 | Assigned | Normal | JioSaavn Lite: Radio not available toast pops up when selected from My Library in Artists section
18029 | Assigned | Minor | JioSaavn Lite: The banner of the song currently playing in the player is changed as JioSaavn logo if opened in pop up view and also when expanded
18030 | Assigned | Minor | JioSaavn Lite:The no results found page is in english even though app language is marathi
18031 | Assigned | Normal | JioSaavn Lite: For other display languages few components remain in English.
18032 | Assigned | Normal | JioSaavn Lite: For regional language, the "save" for music language and "Yes/No" for logging out is in English
18033 | Assigned | Minor | JioSaavn Lite: Even if on boarding language is Hindi, the toast for "Password does not match!" while signing up is in English while creating account
18034 | Assigned | Normal | JioSaavn Lite: For Marathi display language, user can see "My Library" translated text but for English display language only "MyLib"
18035 | Assigned | Normal | JioSaavn Lite: No option to view the password (eye icon) while signing up [Enhancement]
18036 | Assigned | Major | JioSaavn Lite: If the user kills the app and then clicks on the song in the notification bar the user is been told to login again
18037 | Assigned | Major | JioSaavn Lite: If clicked on forgot while logging in, the user is taken to different UI and can play any songs even if not logged in
18038 | Assigned | Normal | JioSaavn Lite: For Regional display language, the description for clear player is in English
18039 | Assigned | Normal | JioSaavn Lite: For regional display language,the toasts for clicking thumbs down icon in channels is in English
18040 | Assigned | Minor | JioSaavn Lite: Description below the phone number field while signing up when selected on boarding language is Bhojpuri, gets translated after changing the country code
18041 | Assigned | Critical | JioSaavn Lite: App crashes when played the song from notification tile and clicked on phone number after killing the app from background
18042 | Assigned | Minor | JioSaavn Lite: While selecting the on boarding language the 2nd line of the above description is missing for some languages
18043 | Assigned | Normal | JioSaavn Lite: In channels on clicking the channel kids nothing happens
18044 | Assigned | Normal | JioSaavn Lite: After changing the app language to marathi the set as jiotune option for some song is still in english
18045 | Assigned | Normal | JioSaavn Lite: Pop up is in english if a user is adding a song in queue and my app language is marathi
18046 | Assigned | Minor | JioSaavn Lite : Mobile navigation overlaps on the list at the bottom of the screen
18047 | Assigned | Normal | JioSaavn Lite: When the user tries to play the 2nd song from notification bar, first song is been played
18349 | Assigned | Major | JioSaavn Lite: Terms & Conditions and Privacy Policy not present on 'Login with Email' and 'create account' page
18350 | Assigned | Minor | JioSaavn Lite: There is a green patch observed when user scrolls down the shows list in a podcast.
18351 | Assigned | Normal | JioSaavn Lite: User can't scroll over the display language page when app is used in split screen mode.
18352 | Assigned | Normal | JioSaavn Lite:If the song is been currently played user can observe that there is a play symbol in the notification bar
18353 | Assigned | Normal | JioSaavn Lite: Unable to close the popup of JioTune when opened the app in popup view [Device Specific]
18354 | Assigned | Minor | JioSaavn Lite: The Translation of word "Rainy" is incorrect in some display languages.
18355 | Assigned | Major | JioSaavn Lite: Jiotunes not available when switched to Wifi even after ZLA login
18356 | Assigned | Minor | JioSaavn Lite:Few components such as "artist radio" are not been converted into marathi if app language is marathi
18357 | Assigned | Minor | JioSaavn Lite : "TrendingJiotunes" should be separated by spaces.
18358 | Assigned | Minor | JioSaavn Lite : White padding at top is observed on page redirected after clicking "More Trending JioTunes"
18359 | Assigned | Minor | JioSaavn Lite: Names of songs and playlists changes to English when user clicks on "More Songs" and "More Playlists".
18360 | Assigned | Normal | JioSaavn Lite: User is not able to pause the song from the notification bar once logged out
18363 | Assigned | Normal | JioSaavn Lite:The text overlaps on the login page if user maximise the app from the freeform mode(Device Specific:Oneplus 8T)
18369 | Assigned | Major | JioSaavn Lite: When outside app and clicked on the song from notification tray shows "loading data..." indefinitely
18373 | Assigned | Minor | JioSaavn Lite: Some text in the login page is cropped when display language is Malayalam.
18374 | Assigned | Minor | JioSaavn Lite: "Loading" message must be as per the display language.
18377 | Assigned | Minor | JioSaavn Lite: Some channels names are incorrect in some display languages.
18380 | Assigned | Minor | JioSaavn Lite: The translation of some texts is incorrect in languages like Hindi, Marathi, Bhojpuri and Haryanvi.
18384 | Assigned | Normal | JioSaavn Lite: Unable to click on app's back button and meatball menu

## Assign Issue
Issue List | Group1 | Group2 | Group3
2 to 14 | Rahul | Rupesh | Mitali
15 to 26 | Ankita | Sakshi | Chirag
27 to 38 | Gaurav1 | Aparna | Roopesh
39 to 50 | Somesh | Rushabh | Tanmay
51 to 62 | Vedant | Khushboo | Harshita
63 to 74 | Vikrant | Priyanka | Shriyansh